## RFP Overview
A13 - TPP Choice Modeling Conjoint RFP Overview
RFP Title | Target Product Profile — Quantitative Concept Testing and Claims Conjoint / Preference Share Modeling
RFP ID | A13-TPP-CONJOINT-2024
Issue Date | March 12, 2026
Submission Deadline | September 9, 2026, 5:00 PM ET
Methodology Type | Conjoint Analysis / Choice Modeling / DCE + Quantitative Concept Testing
Scope | Global - Multiple Therapeutic Areas
Target Audience | Healthcare Professionals (HCPs)
Lifecycle Stage | Pre-launch (Phase II/III)
Research Stages | 2 (TPP Concept Testing + Claims Conjoint)
Therapeutic Areas | 3 (CDiff Vaccine, Diabetes SGLT, Immunology Dupi Asthma)
Cost Templates Required | 6 (2 stages × 3 therapy areas)
Compliance Requirements | SOX Section 404, PV, CSR
Partnership Tiers | Tier 1 (Agency of Record) / Tier 2 (Preferred Partner)
Evaluation Method | Multi-round (written → shortlist → presentations → selection)
Key Timeline Milestones
Milestone | Date | Notes
Questions Deadline | August 23, 2026, 11:59 PM ET | All questions must be submitted in writing
Proposal Submission | September 9, 2026, 5:00 PM ET | E-sourcing platform + email to Procurement
Initial Evaluation | September 20, 2026 | Written proposal review
Shortlist Notification | September 25, 2026 | Selected bidders notified
Presentation Phase | October 2-6, 2026 | Finalist presentations
Final Selection | October 15, 2026 | Winner notification
Contract Execution | November 1, 2026 | MSA and project contracts
ORIGINAL RFP SCHEDULE REFERENCE
Market Research Services Type | Target Product Profile Quantitative Concept Testing & Claims Conjoint / Preference Share Modeling
Date Issued | July 19
Project Type | Multiple
Products | New Product E (Diabetes - SGLT-1/SGLT-2 inhibitor), New Product D (Immunology - Duvalimab asthma), New Product C (Vaccine - C-Diff)
Therapeutic Areas | Diabetes, Immunology, Vaccines
Markets | Key Global Markets - specified per therapy
CONTACTS
Role | Name | Phone | Email
Purchasing Contact | Kiran Harmon | [PHONE] | [CONTACT_EMAIL]
Customer Insights Contact | [See original RFP]

## Cost Breakdown
A13 - Cost Breakdown Template
IMPORTANT: 6 cost templates required (2 Research Stages x 3 Therapy Areas). HCP and Patient/Consumer costs in separate tabs.
These cost breakdowns form the basis of a standard rate card for MSA negotiation.
Template: Stage [1/2] - Therapy Area [CDiff/Diabetes SGLT/Dupi Asthma] - Audience [HCP/Patient]
Cost Category | Cost Driver / Line Item | Unit Cost | Quantity | Total Cost | Currency | Notes
A. Project Initiation
| Project design & methodology |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Questionnaire / guide development |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Questionnaire programming |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Translation / localization |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
B. Fieldwork Preparation
| Scheduling / logistics |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Interviewer briefing & instructions |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Print / mail / materials |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Pilot / soft launch |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
C. Fieldwork
| Recruitment / screening |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Data collection (interviewing) |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Respondent incentives / honoraria |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Validation / quality control |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Compliance / monitoring |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
D. Data Processing
| Code building |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Coding (open-ends) |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Data entry / cleaning |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Tabulation / cross-tabs |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
E. Analytics
| Statistical analysis / modeling |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Conjoint / choice modeling (Stage 2) |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Simulator development (Stage 2) |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Normative benchmarking |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Sensitivity analysis |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
F. Reporting & Deliverables
| Topline / interim report |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Final report & presentation |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Executive summary |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Implementation workshop materials |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
G. Overheads & Other
| Project management |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Travel & expenses |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Technology / platform costs |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
| Contingency (10-15%) |  |  | [VENDOR TO COMPLETE] | [SELECT: USD¦EUR¦GBP]
TOTAL (All-inclusive)
RATE CARD FOR MSA NEGOTIATION
Role / Service | Hourly Rate | Daily Rate | Notes
Senior Consultant / Partner | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE]
Project Director | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE]
Project Manager | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE]
Analyst / Researcher | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE]
Statistical Analyst | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE]
Fieldwork / Data Collection | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE]

## Markets & Sample
A13 - Markets & Sample Requirements
Geographic Scope: Global
Primary Target Audience: Healthcare Professionals (HCPs)
HCP Segment | Specialties | Setting | Sample Requirements
Primary Care | Family medicine, internal medicine | Private practice, clinics | Representative of patient volume
Specialists | Endocrinologists, immunologists, ID specialists | Hospitals, specialty centers | Key opinion leaders included
Hospital-based | Various specialties | Academic medical centers | Institution representation
Academic | Research-oriented physicians | Universities, research centers | Innovation adoption leaders
Sample Size Guidelines
Research Component | Minimum Sample | Target Sample | Rationale
TPP Concept Testing | 200 per market | 300 per market | Statistical power for concept testing
Claims Conjoint | 150 per market | 250 per market | Reliable preference modeling
Key Markets per TA | 3-5 markets | 5-7 markets | Geographic representation
Total HCPs per TA | 600-1,000 | 1,000-1,500 | Robust segmentation analysis

## Vendor Capabilities
A13 - Required Vendor Capabilities
Core Methodological Capabilities
Capability Area | Required Skills | Experience Level | Validation Requirements
Conjoint Analysis | CBC, MaxDiff, BWS, adaptive conjoint | 10+ large-scale studies | Case studies with validation
Choice Modeling | Discrete choice experiments, MNL, HB | Pharma experience preferred | Predictive accuracy demonstrated
Concept Testing | Quantitative concept validation | Healthcare experience | Normative benchmarks
Preference Share Modeling | Market simulation, sensitivity analysis | Launch forecasting experience | Accuracy case studies
HCP Research | Physician recruitment and engagement | Global HCP panels | Quality controls
Statistical Analysis | Advanced analytics, segmentation | PhD-level statisticians | Peer-reviewed publications
Technology Platform | Interactive simulators, dashboards | User-friendly interfaces | Technical documentation
Project Management | End-to-end coordination | Consultative approach | Stakeholder management
Compliance & Regulatory Capabilities
Compliance Area | Requirements | Documentation Needed
SOX Section 404 | System controls, change management, security | SOPs, audit trails, certifications
Pharmacovigilance (PV) | AE reporting, safety data collection | Training records, procedures, contacts
Data Privacy | GDPR, HIPAA, local regulations | Privacy policies, security measures
Quality Systems | ISO certifications, quality controls | Certificates, quality manuals
Corporate Social Responsibility | Sustainability, ethics, diversity | CSR reports, policies, initiatives

## Timeline & Milestones
A13 - Project Timeline & Milestones
RFP Process Timeline
Phase | Activity | Date | Duration | Responsibility | Notes
Issue | RFP Release | March 12, 2026 | 1 day | [CLIENT_ORG] | Full RFP package available
Questions | Clarification Period | Aug 23, 2026 | 3 weeks | Bidders | Written questions only
Submission | Proposal Deadline | Sep 9, 2026 | 1 day | Bidders | E-sourcing + email required
Evaluation | Initial Review | Sep 20, 2026 | 2 weeks | [CLIENT_ORG] | Written proposal scoring
Shortlist | Finalist Selection | Sep 25, 2026 | 1 week | [CLIENT_ORG] | Top 3-5 bidders selected
Presentations | Finalist Presentations | Oct 2-6, 2026 | 1 week | Finalists | In-person or virtual
Selection | Final Decision | Oct 15, 2026 | 1 week | [CLIENT_ORG] | Winner notification
Contracting | MSA Execution | Nov 1, 2026 | 2 weeks | Both parties | Legal and commercial terms
Typical Project Execution Timeline (Post-Award)
Stage | Activity | Duration | Key Deliverables
Kickoff | Project initiation and planning | 2 weeks | Project plan, study design
Stage 1 | TPP Concept Testing | 8-12 weeks | Concept testing results, recommendations
Stage 2 | Claims Conjoint Study | 10-14 weeks | Preference share model, simulator
Integration | Cross-stage analysis | 2-4 weeks | Integrated insights, implications
Implementation | Business implementation support | 2-4 weeks | Workshop materials, training
Total Duration | End-to-end project | 24-36 weeks | Complete research program

## Evaluation Scorecard
A13 - Evaluation Scorecard
Note: Per original RFP, 'the order does not reflect the importance of each criteria.' Weights below are suggested for internal use.
Criterion | Weight (%) | Vendor A (1-5) | Vendor A Weighted | Vendor B (1-5) | Vendor B Weighted | Vendor C (1-5) | Vendor C Weighted
Expertise & track record in implementing such services | [INTERNAL] | [EVALUATOR] |  | [EVALUATOR] |  | [EVALUATOR]
Client feedback / references for similar projects | [INTERNAL] | [EVALUATOR] |  | [EVALUATOR] |  | [EVALUATOR]
Flexibility of the bidder | [INTERNAL] | [EVALUATOR] |  | [EVALUATOR] |  | [EVALUATOR]
Understanding of context and RFP requirements | [INTERNAL] | [EVALUATOR] |  | [EVALUATOR] |  | [EVALUATOR]
Quality, clarity and compliance of proposal format | [INTERNAL] | [EVALUATOR] |  | [EVALUATOR] |  | [EVALUATOR]
Relevance and accuracy to expressed requirements | [INTERNAL] | [EVALUATOR] |  | [EVALUATOR] |  | [EVALUATOR]
Research methods with norms/benchmarks and/or in-market validation | [INTERNAL] | [EVALUATOR] |  | [EVALUATOR] |  | [EVALUATOR]
Innovative yet disciplined and rigorous methods | [INTERNAL] | [EVALUATOR] |  | [EVALUATOR] |  | [EVALUATOR]
Quality of proposed Service Levels and commitments | [INTERNAL] | [EVALUATOR] |  | [EVALUATOR] |  | [EVALUATOR]
General qualifications (geographic presence, size, stability) | [INTERNAL] | [EVALUATOR] |  | [EVALUATOR] |  | [EVALUATOR]
Financial conditions (total cost, variability, risk, rate card transparency, savings, cash generation) | [INTERNAL] | [EVALUATOR] |  | [EVALUATOR] |  | [EVALUATOR]
Acceptance of contractual template terms | [INTERNAL] | [EVALUATOR] |  | [EVALUATOR] |  | [EVALUATOR]
PV compliance (AE identification & reporting within 24 hours) | [INTERNAL] | [EVALUATOR] |  | [EVALUATOR] |  | [EVALUATOR]
Fair market value alignment | [INTERNAL] | [EVALUATOR] |  | [EVALUATOR] |  | [EVALUATOR]
TOTAL WEIGHTED SCORE

## Sample Projects
A13 - Sample Project Portfolio
Please provide 3-5 relevant project examples demonstrating required capabilities.
Project Type | Therapy Area | Methodology | Sample Size | Markets | Outcome | Validation
[VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE]
[VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE]
[VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE]
[VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE]
[VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE] | [VENDOR TO COMPLETE]